## Light
PROJECT: iCARE++
Batangas State University – TNEU ARASOF Nasugbu |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Linux Adona ¦ Andre Cachola ¦ Xyreel Laguras
Project start date: | 2026-05-20 |  |  |  |  | May | [13 empty] | June | [27 empty] | July
Scrolling increment: | 99 | time axis 2026-05-20 to 2026-07-31
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2026-05-20 to 2026-07-31
PHASE 1: SYSTEM DEVELOPMENT
Web Application (Next.js + Supabase) | On Track | Linux Adona | 100% | 2026-05-20 | 132
└ UI/UX Design & Wireframing | On Track | Linux Adona | 100% | 2026-05-20 | 21
└ Role Dashboards (Instructor, Dean, Admin) | On Track | Linux Adona | 100% | 2026-06-10 | 51
└ Sections, Groups & Ward Floor Plan | On Track | Linux Adona | 100% | 2026-07-31 | 35
└ Analytics Dashboards & Reports | On Track | Linux Adona | 100% | 2026-09-04 | 25
Backend API & Database (Next.js Route Handlers + Supabase Postgres) | On Track | Linux Adona | 100% | 2026-05-20 | 132
└ Database Schema Design & Migrations | On Track | Linux Adona | 100% | 2026-05-20 | 28
└ REST API Endpoint Development | On Track | Linux Adona | 100% | 2026-06-17 | 45
└ Authentication, Roles, Google Sign-in & Session Hardening | On Track | Linux Adona | 100% | 2026-08-01 | 31
└ API Documentation (Postman Collection) | On Track | Linux Adona | 100% | 2026-09-01 | 28
ML-Based Student Performance Prediction (FastAPI) | On Track | Linux Adona | 100% | 2026-06-10 | 81
└ Data Collection & Preprocessing | On Track | Linux Adona | 100% | 2026-06-10 | 21
└ Model Training & Evaluation (Low-Performing Prediction) | On Track | Linux Adona | 100% | 2026-07-01 | 24
└ Learning Recommendation Engine | On Track | Linux Adona | 100% | 2026-07-25 | 14
└ Web Integration & ML Job Runs | On Track | Linux Adona | 100% | 2026-08-08 | 22
AI-Assisted Learning Features | On Track | Linux Adona | 100% | 2026-07-01 | 90
└ AI Provider Chain (Claude → Gemini → OpenRouter) & Usage Metrics | On Track | Linux Adona | 100% | 2026-07-01 | 21
└ Student AI Study Tips | On Track | Linux Adona | 100% | 2026-07-22 | 25
└ Instructor AI Performance Summaries | On Track | Linux Adona | 100% | 2026-08-16 | 23
└ Lesson Import for Taylor's-Grounded Generation | On Track | Linux Adona | 100% | 2026-09-08 | 21
Adaptive Quizzes (Taylor's-Grounded) | On Track | Xyreel Laguras | 100% | 2026-06-17 | 104
└ Question Banks & 18 Chapter Competencies | On Track | Xyreel Laguras | 100% | 2026-06-17 | 35
└ Adaptive Assessment Logic & Scoring | On Track | Linux Adona | 100% | 2026-07-22 | 31
└ Quiz Assignment & Group Visibility | On Track | Xyreel Laguras | 100% | 2026-08-22 | 21
└ Quiz Testing & Feedback | On Track | Andre Cachola | 100% | 2026-09-12 | 17
Patient Cases & RetDem Evaluation | On Track | Linux Adona | 100% | 2026-07-01 | 90
└ Patient Case Library by Taylor's Chapter | On Track | Linux Adona | 100% | 2026-07-01 | 31
└ Case Presentations | On Track | Linux Adona | 100% | 2026-08-01 | 27
└ Skills-Checklist Grading with Verbal Ratings | On Track | Linux Adona | 100% | 2026-08-28 | 16
└ RetDem Timer & Grade-Edit Approval | On Track | Linux Adona | 100% | 2026-09-13 | 16
Mobile Application (Expo / React Native) | On Track | Linux Adona | 100% | 2026-06-10 | 111
└ Mobile UI/UX Design | On Track | Linux Adona | 100% | 2026-06-10 | 21
└ Core Screens (Tasks, Quizzes, Library) | On Track | Linux Adona | 100% | 2026-07-01 | 45
└ API Integration & Local Caching | On Track | Linux Adona | 100% | 2026-08-15 | 28
└ EAS Builds & Device Testing | On Track | Andre Cachola | 100% | 2026-09-12 | 17
Data Warehouse & Analytics | On Track | Xyreel Laguras | 100% | 2026-07-01 | 90
└ Star-Schema Data Warehouse | On Track | Xyreel Laguras | 100% | 2026-07-01 | 21
└ ETL Pipeline with Pruning | On Track | Linux Adona | 100% | 2026-07-22 | 28
└ Classroom Performance & Leaderboard | On Track | Linux Adona | 100% | 2026-08-19 | 24
└ Super Admin Portal & Live Telemetry | On Track | Linux Adona | 100% | 2026-09-12 | 17
System Testing | On Track | Andre Cachola | 100% | 2026-09-01 | 28
└ Playwright Frontend E2E Suite | On Track | Andre Cachola | 100% | 2026-09-01 | 10
└ Postman API Test Collection | On Track | Andre Cachola | 100% | 2026-09-11 | 7
└ Performance Monitoring & Benchmarking | On Track | Andre Cachola | 100% | 2026-09-18 | 5
└ Bug Fixes & Regression Testing | On Track | Andre Cachola | 100% | 2026-09-23 | 6
PHASE 2: PRE-ORAL DEFENSE & REVISIONS
Pre-Oral Defense | Milestone | All Members | 100% | 2026-09-29 | 1
Incorporate Panel's Suggestions | On Track | Linux Adona | 0% | 2026-09-30 | 6
Checking of the Developed System | Milestone | All Members | 0% | 2026-10-06 | 1
PHASE 3: PILOT TESTING & EVALUATION
Live Pilot Testing – Nursing Program | On Track | Andre Cachola | 0% | 2026-10-07 | 13
└ Pilot Deployment & Account Setup | On Track | Linux Adona | 0% | 2026-10-07 | 1
└ Instructor Questionnaire Validation | Milestone | Xyreel Laguras | 0% | 2026-10-12 | 1
└ Questionnaire Administration & Data Gathering | On Track | Andre Cachola | 0% | 2026-10-13 | 7
Results Analysis & Effectiveness Evaluation | On Track | Xyreel Laguras | 0% | 2026-10-20 | 5
PHASE 4: DOCUMENTATION & FINAL DEFENSE
Manuscript & Documentation Revisions | On Track | Xyreel Laguras | 0% | 2026-10-20 | 12
└ Chapter 4–5 Results & Discussion Write-up | On Track | Xyreel Laguras | 0% | 2026-10-20 | 7
└ Adviser Review & Final Revisions | On Track | Xyreel Laguras | 0% | 2026-10-27 | 5
Final Defense Preparation | On Track | All Members | 0% | 2026-11-01 | 6
Final Defense | Milestone | All Members | 0% | 2026-11-07 | 1
To add more data, Insert new rows ABOVE this one